## Slide 1: Community Assistance Center Update May 2, 2016
By Elaine Wiseman, City of Reno
Kevin Schiller, Washoe County

## Slide 2: Overflow Update
Overflow building was vandalized and became uninhabitable on February 20, 2016. We have opened a temporary overflow on the 2nd floor of the CAC; converting the storage room to a sleeping area that can accommodate 48 people. We are aggressively looking at potential buildings; however have not been successful in securing a location.
As a direct result of the loss of the overflow shelter, we have seen a tremendous increase in the number of camps along the river, particularly in Sparks.
Sparks recently passed their “no camping” ordinance; however are unable to exercise enforcement due to not having an overflow.

## Slide 3: CAC Updates (Physical Improvements) 12/9/15 slide
Updates to existing lighting as well as new lighting fixtures to be complete by January 31, 2016 (parking lot)
Complete
Security door at Men’s Shelter will be installed this month
Complete
Upgrades to security cameras will be complete by January 31, 2016
In progress

## Slide 4: RFP for Shelter Operations
RFP Release | February 9, 2016 complete
Mandatory Proposer’s Conference | February 23, 2016 complete
RFP’s Due to City of Reno | March 18, 2016 complete
Rating and Ranking of Proposals | March 22-April 7, 2016 complete
Interviews/Selection of Vendor | April 18, 2016 complete
Approved by TGB | April 29, 2016 complete
Contract Approval by City Council | June 8, 2016

## Slide 5: RFQ for Shelter Operations
Two Proposals were received
WestCare
Volunteers of America
Both agencies were interviewed and rated by the rating committee

## Slide 6: Scoring Matrix
Proposer Experience and Capacity | 25 | 24.2 | 18.8
Program Design | 25 | 21.4 | 18
Community Services Integration | 10 | 8.4 | 7.2
Past Performance | 10 | 9.8 | 7.4
Budget and Financial Stability | 20 | 17.8 | 14
HMIS Participation | 5 | 4.8 | 4.4
Project Readiness | 5 | 5 | 3.4
TOTAL | 100 | 91.4 | 73.2
VOA
WestCare
Points Possible

## Slide 7: General Details...
Inclusion of year-round overflow with programming
An individual assessment which will be used to triage each client to appropriate programs within the entire spectrum of care within our community
The development of close, collaborative relationships with service providers (for example VOA and CCNN have an MOU regarding Crossroads beds)
Addition of Housing Specialist and Employment Specialist
Utilization of Coordinated Entry and a standardized assessment

## Slide 8
The Transitional Governing Board approved Volunteers of America as the selected operator of the Community Assistance Center for FY 16/17, 17/18, 18/19
Contract with VOA for Shelter Operations will be brought before Reno City Council on June 8, 2016

## Slide 9
VOA’s proposal includes enhanced services with the inclusion of a year-round overflow and increased case management. With these additional services, the funding request has increased.
Goal to meet VOA’s proposal= $2,650,858
Prior funding at approximately 1.9 million, per established budget in 2009.

## Slide 10: Funding Formula
 | Reno | Sparks | Washoe County | TOTAL
Current 16/17 | .005 $368,491 | .005 $132,020 | .01 $1,347,237 | $1,847,748
Option A | .01 $736,982 | .01 $264,040 | .0125 (+$336,809) $1,684,046 | $2,685,068
Option B | .01 $736,982 | .01 $264,040 | .015 (+673,619) $2,020,856 | $3,021,878
On April 29, 2016 the Transitional Governing Board moved to approve Option B as their recommendation for the new funding formula.

## Slide 11
Next Steps
Staff recommends the Washoe County Commission, Reno City Council and Sparks City Council motion to accept the Transitional Governing Board’s recommendation to revise the funding formula as follows:
-Washoe County increases their yearly contribution to a .015 (1 ½ cent) value
-Reno increases their yearly contribution to a .01 (1 cent) value
-Sparks increases their yearly contribution to a .01 (1 cent) value
The Transitional Governing Board moved to recommend staff explore the reassignment of the Lead Agency and bring back a recommendation January 2017.

## Slide 12
Questions?